## Color
LMS
Maltepe University |  | Yusra |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Prof. Volkan TUNALI |  | Sami
Project Start Date: | 2022-05-13 | Abdulaziz |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling Increment: | 1 | time axis 2022-05-14 to 2022-07-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-05-14 to 2022-07-08
Week 1
learn mongo db | Goal | All Members | 25% | 2022-05-13 | 3 | 2022-05-14: 2; 2022-05-15: 2
learn mongo db | Milestone | All Members | 75% | 2022-05-14 | 1 | bar: 2022-05-14
desgining database Mongodb | High Risk | All Members | 50% | 2022-05-15 | 10
connection mongoDb | High Risk | All Members | 50% | 2022-05-16 | 1
connection mongoDb | High Risk | All Members | 100% | 2022-05-17 | 6
Week 2
complete and fix DB design | On Track | All Members | 100% | 2022-05-18 | 13
load operations | Med Risk | Yusra | 80% | 2022-05-19 | 9
insert operations | Low Risk | Sami | 33% | 2022-05-20 | 11
delete operation | Milestone | abdulaziz | 45% | 2022-05-21 | 1 | bar: 2022-05-21
Update Operation | Med Risk | whofinishes | 10% | 2022-05-22 | 24
Week 3
load operations | Goal | yusra | 100% | 2022-05-22 | 4 | 2022-05-22: 2; 2022-05-23: 2; 2022-05-24: 2; 2022-05-25: 2
updating,deleting | On Track | sami | 100% | 2022-05-23 | 14
inserting | Goal | azoz, yusra | 100% | 2022-05-24 | 6 | 2022-05-24: 2; 2022-05-25: 2; 2022-05-26: 2; 2022-05-27: 2; 2022-05-28: 2; 2022-05-29: 2
borrowing, returning | Goal | yusra, sami | 100% | 2022-05-22 | 3 | 2022-05-22: 2; 2022-05-23: 2; 2022-05-24: 2
report writing | Low Risk | All Members | 100% | 2022-05-23 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-25 | 15
Task 2 |  |  |  | 2022-06-08 | 5
Task 3 | Milestone |  |  | 2022-07-20 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one